| Date | Day | Task | Volunteers  | Comments |
| --- | --- | --- | --- | --- |
| 5/31/14 | Saturday | * Remove wall Paper
	+ Kitchen
	+ Toy Room
	+ Office
	+ Camille’s Room-Border Only
 | Andy (after Fun Run) | Need 2-6 volunteers |
| 6/2-5/2014 |  | * Cabinet delivery, store on porch
 |  | Jenny Volk to call with delivery date. Unloaded by delivery persons |
| 6/5/14 | Thursday | * Help Pack-up Leah’s office
 |  | Need 1-2 volunteers and a few boxes |
| 6/7/14 | Saturday | * Help Pack-up Kitchen
 |  | Need 1-2 volunteers and a few boxes |
| 6/8/14 | Sunday 2PM to 5PM | * Remove Kitchen Cabinets to Garage
 | Andy | The Hamilton’s will be leaving before 2PMNeed 2-3 volunteers |
| 6/9/14 | Monday | * Install Blocking for new cabinets in Kitchen
 | Chip Andy |  |
| 6/9/14 | Monday | * Rough-in Electrical Kitchen
 | Rick Gomez |  |
| 6/9/14 to 6/13/14 | Monday to Friday | * Remove any remaining wall paper.
* Repair and re-plaster walls and ceilings
 | Dan’s Plastering | Finish Kitchen as soon as possible after electrical rough in and blocking are complete. |
| 6/14 to 6/15 | Saturday | * Prime paint Kitchen Walls and ceiling
 |  | Need 2-4 volunteers |
| 6/15 | Sunday | * Finish paint Kitchen Walls and ceiling
 |  | Need 2-4 volunteers |
| 6/14 to 6/18 | Saturday to Wednesday | * Prime paint walls and ceilings
	+ Office-walls only
	+ Living Room
	+ Dining Room
	+ Toy Room/Bathroom
	+ Camille’s Room
* Finish Paint Ceilings
	+ Living Room
	+ Dining Room
	+ Toy Room/Bathroom
	+ Camille’s Room
 |  | The list is prioritized.As the Hamilton’s will be away, we have access to the house at (most) any time. Anyone wishing to volunteer please call Andy at 482-4313. |
| 6/16 to 6/17 |  | * Install Kitchen Cabinets
* Install Dishwasher and Sink
 | ChipAndy | Could use 1-2 more volunteers. |
| 6/18/2014 |  | * Install Kitchen Floor
 | Able Flooring |  |
| 6/20/14 |  | * Hamilton’s return
 |  |  |