| Date | Day | Task | Volunteers | Comments |
| --- | --- | --- | --- | --- |
| 5/31/14 | Saturday | * Remove wall Paper   + Kitchen   + Toy Room   + Office   + Camille’s Room-Border Only | Andy (after Fun Run) | Need 2-6 volunteers |
| 6/2-5/2014 |  | * Cabinet delivery, store on porch |  | Jenny Volk to call with delivery date. Unloaded by delivery persons |
| 6/5/14 | Thursday | * Help Pack-up Leah’s office |  | Need 1-2 volunteers and a few boxes |
| 6/7/14 | Saturday | * Help Pack-up Kitchen |  | Need 1-2 volunteers and a few boxes |
| 6/8/14 | Sunday 2PM to 5PM | * Remove Kitchen Cabinets to Garage | Andy | The Hamilton’s will be leaving before 2PM  Need 2-3 volunteers |
| 6/9/14 | Monday | * Install Blocking for new cabinets in Kitchen | Chip  Andy |  |
| 6/9/14 | Monday | * Rough-in Electrical Kitchen | Rick Gomez |  |
| 6/9/14 to 6/13/14 | Monday to Friday | * Remove any remaining wall paper. * Repair and re-plaster walls and ceilings | Dan’s Plastering | Finish Kitchen as soon as possible after electrical rough in and blocking are complete. |
| 6/14 to 6/15 | Saturday | * Prime paint Kitchen Walls and ceiling |  | Need 2-4 volunteers |
| 6/15 | Sunday | * Finish paint Kitchen Walls and ceiling |  | Need 2-4 volunteers |
| 6/14 to 6/18 | Saturday to Wednesday | * Prime paint walls and ceilings   + Office-walls only   + Living Room   + Dining Room   + Toy Room/Bathroom   + Camille’s Room * Finish Paint Ceilings   + Living Room   + Dining Room   + Toy Room/Bathroom   + Camille’s Room |  | The list is prioritized.  As the Hamilton’s will be away, we have access to the house at (most) any time.  Anyone wishing to volunteer please call Andy at 482-4313. |
| 6/16 to 6/17 |  | * Install Kitchen Cabinets * Install Dishwasher and Sink | Chip  Andy | Could use 1-2 more volunteers. |
| 6/18/2014 |  | * Install Kitchen Floor | Able Flooring |  |
| 6/20/14 |  | * Hamilton’s return |  |  |